## Slide 1: Steering Committee Update - July 20, 2025

## Slide 2: 1. Overall Portfolio Summary
Overall Status: Amber
  Highlights: Project Phoenix is making excellent progress and is on track for its alpha release. The new UI components are receiving positive feedback from early testing.
  Concerns: Project Titan is currently facing significant challenges with its database migration, which has caused delays and requires immediate attention. Project Apollo’s start date is pending resource availability.

## Slide 3: 2. Project Deep Dive: Project Phoenix
  Status: Green / On-track
  Budget: $450,000 / $500,000 (90% consumed)
  Timeline: On schedule
Key Achievements: * Completed UI overhaul for the main dashboard. * Integrated new charting library.
Upcoming Milestones: * Phoenix Alpha Release: Due July 30, 2025 - On Track
Risks: * Medium Impact: Key designer is on unexpected leave for 2 weeks. Mitigation: Reallocated another designer from a lower-priority project.

## Slide 4: 3. Project Deep Dive: Project Titan
  Status: Red / At-risk
  Budget: $1,100,000 / $1,200,000 (92% consumed)
  Timeline: 4 weeks behind schedule
Key Issues: * The backend refactor is blocked due to unforeseen complexity in the legacy database.
Upcoming Milestones: * Titan DB Migration: Due August 15, 2025 - Overdue
Risks: * High Impact: The current team lacks the specialized skills to address the database migration challenges. This could lead to further delays and budget overruns.

## Slide 5: 4. Key Risks & Issues
Project | Risk Description | Impact | Owner
Project Titan | Specialized database skills needed for migration | High | John Doe
Project Phoenix | Key designer on leave | Medium | Jane Smith

## Slide 6: 5. Decisions Needed
  Project Titan: Approve an additional $50,000 for a specialized database consultant to unblock the migration.
  Portfolio: Confirm the prioritization of Project Apollo for a Q4 2025 start.

## Slide 7: 6. Team & Resource Update
  Team Hercules (Project Titan): Currently overallocated by 20% due to the ongoing database issues.
  Team Pegasus (Project Phoenix): Operating at 95% capacity. Performing well.

## Slide 8: 7. Financial Overview
Project | Budget | Actuals | Variance
Project Phoenix | $500,000 | $450,000 | -$50,000
Project Titan | $1,200,000 | $1,100,000 | -$100,000
Total | $1,700,000 | $1,550,000 | -$150,000